## Data table
Year | Month | Project ID Number | Project Name | Status | Project Value | Project Descriptions | Project Type | Priority | Substatus | Project Manager | Developers | Business Analyst | Next Action | ITQA | FTE Savings | Working Hours | Start date | Dev Start Date | Internal Testing Date | Target Client Testing Date | Target Deployment Date | Actual Deployment Date | Manager Comments
2025 | Jul | 1097198 | The Experienced dude Static Startup 8 | Not Active | 923614 | The Social Experiment Coding League Center for Creative Coding The Network Linkage, Inc. | Operations | Normal | Completed | Jean Zac | Ahmed Daz | Scot Bridgeton | Mary Frittle | QA Tester 3 | 204 | 89.2484 | 2023-05-08 | 1900-01-08 | 2023-09-10 | 2023-10-11 | 2023-12-13 | 2023-12-14 | The Domain of Work Wombat Annual Award Show The Successful Project Software ChasersThe Domain of Work Wombat Annual Award Show The Successful Project Software ChasersImpact Training The Network Excalibur Training
2023 | Jan | 1057420 | The Art of Codes The Coding Master | Active | 1717082 | Mentee to Mentor Mo-Money Masterclass The GFI with Codes Active Achievement Impact Training | Fast Path | Normal | New | Ali Adam | Ahmed Daz | Gerland Singh | Matthew Krillen | QA Tester 2 | 279 | 1569.1421 | 2023-05-14 | 2023-05-15 | 2023-09-16 | 2023-10-17 | 2023-12-19 | 2023-12-20 | Coding Region The Principal of Change The Coding Expert Mentee to Mentor Mo-Money MasterclassCoding Region The Principal of Change The Coding Expert Mentee to Mentor Mo-Money MasterclassActive Achievement Impact Training Code Change Group Excel and Elevate Training Excalibur Training
2024 | Apr | 1097192 | The Experienced dude Static Startup 12 | Active | 77964 | The Social Experiment Coding League Center for Creative Coding The Network Linkage, Inc. | Security | Normal | Completed | Suzan Mike | Ahmed Daz | Daniel Francis | Jean Coombs | QA Tester 2 | 293 | 1071.2748 | 2023-05-18 | 2023-05-19 | 2023-09-20 | 2023-10-21 | 2023-12-23 | 2023-12-24 | Project Explained Code Change Group Box of Crayons The Social Experiment Coding LeagueProject Explained Code Change Group Box of Crayons The Social Experiment Coding LeagueThe Network Linkage, Inc. Enter Coding Town Hall Meeting Switch and Swift
2024 | Dec | 1191179 | The Experienced dude Static Startup 18 | Active | 1887613 | Town Hall Meeting Switch and Swift Fast Coding Coding Region The Principal of Change | Security | Normal | Testing - Client | Suzan Mike | Ahmed Daz | Daniel Francis | Jean Coombs | QA Tester 2 | 304 | 157.8722 | 2023-05-21 | 2023-05-22 | 2023-09-23 | 2023-10-24 | 2023-12-26 | 2023-12-27 | The Network Linkage, Inc. Enter Coding Town Hall Meeting Switch and SwiftThe Network Linkage, Inc. Enter Coding Town Hall Meeting Switch and SwiftCoding Region The Principal of Change The Coding Expert Mentee to Mentor Mo-Money Masterclass
2023 | Jun | 1154635 | Wide Stringer White Feather | Active | 518169 | The Experienced dude Static Startup The Art of Codes | Security | Normal | Resource Assignment | Eddy Verly | Ahmed Daz | Daniel Francis | Bobby Guillman | QA Tester 2 | 311 | 146.0233 | 2023-05-22 | 2023-05-23 | 2023-09-24 | 2023-10-25 | 2023-12-27 | 2023-12-28 | Mentee to Mentor Mo-Money Masterclass Town Hall Meeting Active Achievement Impact TrainingMentee to Mentor Mo-Money Masterclass Town Hall Meeting Active Achievement Impact TrainingJava Dalia The Successful Project Static Startup
2025 | Nov | 1214146 | The GFI with Codes The Coding Expert | Not Active | 1280291 | Social Geek Made Box of Crayons Moving Bird Made by Me Center for Creative Coding | Operations | High | Completed | Ali Adam | Ahmed Daz | Mei Lee | Eddy Vertil | QA Tester 9 | 56 | 1945.9375 | 2023-06-07 | 2023-06-08 | 2023-10-10 | 2023-11-10 | 2024-01-12 | 2024-01-13 | The Blue Bird The Experienced dude Search Engine Bandits In Recognition of Codes Social Geek Made Box of CrayonsThe Blue Bird The Experienced dude Search Engine Bandits In Recognition of Codes Social Geek Made Box of CrayonsMade by Me Center for Creative Coding The Blue Bird The Discovery of Era Enter Coding
2024 | Sep | 1082321 | New Workers Excel and Elevate Training | Active | 966555 | Fast & Creative Gang Gob Geeklords The Domain of Work The Coding Master Celestial Interface | Operations - Global | Normal | Testing - Ops | Eddy Verly | Ahmed Daz | Whittney Huttson | Alison Cookadee | QA Tester 3 | 245 | 1952.5214 | 2023-06-23 | 2023-06-24 | 2023-10-26 | 2023-11-26 | 2024-01-28 | 2024-01-29 | The Successful Project Software Chasers 7th Annual Workshop Fast & Creative Gang Gob GeeklordsThe Successful Project Software Chasers 7th Annual Workshop Fast & Creative Gang Gob GeeklordsThe Coding Master Celestial Interface The Successful Project The Art of Codes Open Source Pundits
2024 | Jan | 1097224 | The Experienced dude Static Startup 6 | Active | 1836511 | The Network Linkage, Inc. Enter Coding Town Hall Meeting Switch and Swift | Operations | High | Scheduled for Deployment | Suzan Mike | Ahmed Daz | Whittney Huttson | Project Management | QA Tester 3 | 56 | 1927.8101 | 2023-06-24 | 2023-06-25 | 2023-10-27 | 2023-11-27 | 2024-01-29 | 2024-01-30 | Annual Award Show White Feather A Salute to New Workers 7th Annual Workshop Wide StringerAnnual Award Show White Feather A Salute to New Workers 7th Annual Workshop Wide StringerExcalibur Training Town Hall Meeting Robust Routine
2023 | Feb | 1068524 | The Experienced dude Static Startup 5 | Active | 1841294 | The Coding Master Celestial Interface Debug Entity The Art of Codes Open Source Pundits | Security | Normal | Research | Suzan Mike | Ahmed Daz | Gerland Singh | Jesse Brenderman | QA Tester 3 | 259 | 570.6584 | 2023-07-17 | 2023-07-18 | 2023-11-19 | 2023-12-20 | 2024-02-21 | 2024-02-22 | Match of Health Debug Entity Excel and Elevate Training Annual Award Show White FeatherMatch of Health Debug Entity Excel and Elevate Training Annual Award Show White FeatherThe Network Linkage, Inc. Enter Coding Town Hall Meeting Switch and Swift
2023 | Mar | 1056053 | The Experienced dude Static Startup 6 | Active | 1029185 | The Social Experiment Coding League The Success The Network Linkage, Inc. | Client | Normal | Requirements | Jean Zac | Dany Jr. | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 39 | 226.8646 | 2023-05-07 | 2023-07-08 | 2023-09-09 | 2023-10-10 | 2023-12-12 | 2023-12-13 | Project Explained Code Change Group Meetup for the Good The Social Experiment Coding LeagueProject Explained Code Change Group Meetup for the Good The Social Experiment Coding LeagueThe Network Linkage, Inc. Project Explained Town Hall Meeting Switch and Swift
2025 | Feb | 1097250 | The Experienced dude Static Startup 9 | Active | 618794 | Impact Training The Network Excalibur Training | IT | Normal | Completed | Ali Adam | Dany Jr. | Gerland Singh | Eddy Vertil | QA Tester 2 | 93 | 1785.9045 | 2023-05-10 | 2023-05-11 | 2023-09-12 | 2023-10-13 | 2023-12-15 | 2023-12-16 | The Successful Project Software Chasers 7th Annual Workshop Fast & Creative Gang Gob GeeklordsThe Successful Project Software Chasers 7th Annual Workshop Fast & Creative Gang Gob GeeklordsThe Experienced dude Static Startup Wombat Box of Crayons Indie Profilers
2025 | Dec | 1159463 | Fast & Creative Gang The Successful Project | Not Active | 986779 | Meetup for the Good The Coding Expert Charged by Codes The Success The GFI with Codes | Security | Normal | Completed | Ali Adam | Dany Jr. | Gerland Singh | Matthew Krillen | QA Tester 2 | 276 | 2075.3825 | 2023-05-17 | 2023-05-18 | 2023-09-19 | 2023-10-20 | 2023-12-22 | 2023-12-23 | Remembering Our Ancestors Fast Coding The Art of Codes Meetup for the Good The Coding ExpertRemembering Our Ancestors Fast Coding The Art of Codes Meetup for the Good The Coding ExpertThe Success The GFI with Codes The Experienced dude Project Explained Code Change Group
2025 | Mar | 1067883 | Indie Profilers Static Startup | Not Active | 1597700 | Town Hall Meeting Switch and Swift Fast Coding Coding Region The Principal of Change | Client - Global | Normal | Completed | Ali Adam | Dany Jr. | Mei Lee | Eddy Vertil | QA Tester 3 | 39 | 1663.5297 | 2023-05-31 | 2023-06-01 | 2023-10-03 | 2023-11-03 | 2024-01-05 | 2024-01-06 | A Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityA Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityRobust Routine Coding Region Debug Entity
2024 | Apr | 1098028 | Impact Training Mo-Money Masterclass | Active | 622042 | The Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast Coding | Fast Path | Normal | Research | Suzan Mike | Dany Jr. | Whittney Huttson | Jonny Levitiz | QA Tester 3 | 55 | 1712.3283 | 2023-06-02 | 2023-06-03 | 2023-10-05 | 2023-11-05 | 2024-01-07 | 2024-01-08 | Made by Me Center for Creative Coding Fast & Creative Gang The Discovery of Era Enter CodingMade by Me Center for Creative Coding Fast & Creative Gang The Discovery of Era Enter CodingRemembering Our Ancestors Fast Coding The Art of Codes Meetup for the Good The Coding Expert
2025 | Dec | 1272487 | White Feather Debug Entity | Active | 534194 | The Experienced dude Static Startup Wombat Box of Crayons Indie Profilers | Fast Path | Normal | Completed | Ali Adam | Dany Jr. | Mei Lee | Eddy Vertil | QA Tester 3 | 150 | 1451.7603 | 2023-06-05 | 2023-06-06 | 2023-10-08 | 2023-11-08 | 2024-01-10 | 2024-01-11 | Charged by Codes Java Dalia Wide Stringer The Experienced dude Static StartupCharged by Codes Java Dalia Wide Stringer The Experienced dude Static StartupBox of Crayons Indie Profilers Software Chasers The Blue Bird The Experienced dude Search Engine Bandits
2023 | Mar | 1294081 | Moving Bird In Recognition of Codes | Active | 1920909 | 7th Annual Workshop Wide Stringer Mo-Money Masterclass The Domain of Work Wombat | Client | Normal | Research | Ali Adam | Dany Jr. | Whittney Huttson | Eddy Vertil | QA Tester 3 | 39 | 1004.036 | 2023-06-14 | 2023-06-15 | 2023-10-17 | 2023-11-17 | 2024-01-19 | 2024-01-20 | Annual Award Show White Feather The Principal of Change 7th Annual Workshop Wide StringerAnnual Award Show White Feather The Principal of Change 7th Annual Workshop Wide StringerThe Domain of Work Wombat Impact Training The Successful Project Software Chasers
2025 | Sep | 1080956 | Search Engine Bandits Indie Profilers | Not Active | 1224898 | Robust Routine Coding Region Debug Entity | IT | Normal | Completed | Ali Adam | Dany Jr. | Scot Bridgeton | Bernard Suppremilo | QA Tester 3 | 106 | 103.9829 | 2023-06-17 | 2023-06-18 | 2023-10-20 | 2023-11-20 | 2024-01-22 | 2024-01-23 | Match of Health Debug Entity Excel and Elevate Training Annual Award Show White FeatherMatch of Health Debug Entity Excel and Elevate Training Annual Award Show White Feather
2023 | Apr | 1115640 | The Experienced dude Static Startup 16 | Active | 144333 | The Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob Geeklords | Client | Normal | Task and Hours | Eddy Verly | Dany Jr. | Gerland Singh | William Davis | QA Tester 3 | 56 | 1869.7738 | 2023-06-30 | 2023-07-01 | 2023-11-02 | 2023-12-03 | 2024-02-04 | 2024-02-05 | The Domain of Work Wombat Impact Training The Successful Project Software ChasersThe Domain of Work Wombat Impact Training The Successful Project Software ChasersFast & Creative Gang Gob Geeklords Robust Routine The Coding Master Celestial Interface
2024 | Sep | 1262858 | Wombat Wide Stringer | Active | 1834727 | The Experienced dude Static Startup Wombat Box of Crayons Indie Profilers | Client | Normal | Development - Ops | Ali Adam | Dany Jr. | Scot Bridgeton | William Davis | QA Tester 3 | 361 | 2146.4395 | 2023-07-09 | 2023-07-10 | 2023-11-11 | 2023-12-12 | 2024-02-13 | 2024-02-14 | Fast & Creative Gang Gob Geeklords The Domain of Work The Coding Master Celestial InterfaceFast & Creative Gang Gob Geeklords The Domain of Work The Coding Master Celestial InterfaceThe Success The GFI with Codes The Experienced dude Project Explained Code Change Group
2025 | Aug | 1179138 | Charged by Codes The Art of Codes | Not Active | 1103657 | Mentee to Mentor Mo-Money Masterclass Town Hall Meeting Active Achievement Impact Training | Security | Normal | Completed | Ali Adam | Dany Jr. | Gerland Singh | Matthew Krillen | QA Tester 2 | 269 | 556.1431 | 2023-07-15 | 2023-07-16 | 2023-11-17 | 2023-12-18 | 2024-02-19 | 2024-02-20 | Coding Region The Principal of Change The Network Mentee to Mentor Mo-Money MasterclassCoding Region The Principal of Change The Network Mentee to Mentor Mo-Money MasterclassActive Achievement Impact Training Coding Region Excel and Elevate Training Excalibur Training
2025 | Apr | 1080455 | Match of Health A Salute to New Workers | Not Active | 2047041 | In Recognition of Codes The Art of Codes Annual Award Show Moving Bird Charged by Codes | Security | Normal | Completed | Suzan Mike | Esra Mejid | Daniel Francis | Jean Coombs | QA Tester 2 | 300 | 632.612 | 2023-05-13 | 2023-05-14 | 2023-09-15 | 2023-10-16 | 2023-12-18 | 2023-12-19 | Meetup for the Good The Coding Expert Charged by Codes The Success The GFI with CodesMeetup for the Good The Coding Expert Charged by Codes The Success The GFI with CodesProject Explained Code Change Group Box of Crayons The Social Experiment Coding League
2024 | Jan | 1021647 | Coding League Code Change Group | Active | 135306 | The Art of Codes Open Source Pundits Fast & Creative Gang Charged by Codes Java Dalia | Security | Normal | Approved for Deployment | Jean Zac | Esra Mejid | NA | Bruce Gordon | QA Tester 3 | 263 | 218.3296 | 2023-05-19 | 2023-05-20 | 2023-09-21 | 2023-10-22 | 2023-12-24 | 2023-12-25 | Town Hall Meeting Switch and Swift The Social Experiment Coding Region The Principal of ChangeTown Hall Meeting Switch and Swift The Social Experiment Coding Region The Principal of ChangeCharged by Codes Java Dalia The Coding Master The Experienced dude Static Startup
2025 | Mar | 1189197 | Made by Me Social Geek Made | Active | 1489303 | A Salute to New Workers Robust Routine Active Achievement Match of Health Debug Entity | Client - Global | High | Resource Assignment | Suzan Mike | Esra Mejid | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 79 | 1688.2834 | 2023-05-25 | 2023-05-26 | 2023-09-27 | 2023-10-28 | 2023-12-30 | 2023-12-31 | Excel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineExcel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineMatch of Health Debug Entity Excel and Elevate Training Annual Award Show White Feather
2023 | Aug | 1052501 | The Experienced dude Static Startup 14 | Active | 330428 | The Success The GFI with Codes The Experienced dude Project Explained Code Change Group | IT | Normal | Development - Security | Suzan Mike | Esra Mejid | Mei Lee | Eddy Vertil | QA Tester 3 | 151 | 2001.623 | 2023-06-08 | 2023-06-09 | 2023-10-11 | 2023-11-11 | 2024-01-13 | 2024-01-14 | Meetup for the Good The Coding Expert Charged by Codes The Success The GFI with CodesMeetup for the Good The Coding Expert Charged by Codes The Success The GFI with CodesProject Explained Code Change Group Box of Crayons The Social Experiment Coding League
2025 | Aug | 1185043 | The Blue Bird Moving Bird | Active | 1145021 | 7th Annual Workshop Wide Stringer Match of Health The Domain of Work Wombat | Operations - Global | Normal | Completed | Suzan Mike | Esra Mejid | Gerland Singh | Eddy Vertil | QA Tester 3 | 40 | 1875.0482 | 2023-06-12 | 2023-06-13 | 2023-10-15 | 2023-11-15 | 2024-01-17 | 2024-01-18 | Annual Award Show White Feather A Salute to New Workers 7th Annual Workshop Wide StringerAnnual Award Show White Feather A Salute to New Workers 7th Annual Workshop Wide StringerThe Domain of Work Wombat Annual Award Show The Successful Project Software Chasers
2024 | Jun | 1082423 | Town Hall Meeting The Network | Active | 247782 | Coding Region The Principal of Change The Coding Expert Mentee to Mentor Mo-Money Masterclass | IT | Normal | On Hold | Suzan Mike | Esra Mejid | Gerland Singh | Shakena Underwood | QA Tester 3 | 73 | 1650.1385 | 2023-06-16 | 2023-06-17 | 2023-10-19 | 2023-11-19 | 2024-01-21 | 2024-01-22 | Town Hall Meeting Switch and Swift Fast Coding Coding Region The Principal of ChangeTown Hall Meeting Switch and Swift Fast Coding Coding Region The Principal of ChangeMentee to Mentor Mo-Money Masterclass The GFI with Codes Active Achievement Impact Training
2023 | Oct | 1142401 | Switch and Swift Linkage, Inc. | Active | 154354 | The Blue Bird The Experienced dude Search Engine Bandits In Recognition of Codes Social Geek Made Box of Crayons | Client | Normal | Testing - Ops | Suzan Mike | Esra Mejid | NA | Ashley Queenie | QA Tester 2 | 39 | 449.3593 | 2023-06-22 | 2023-06-23 | 2023-10-25 | 2023-11-25 | 2024-01-27 | 2024-01-28 | Box of Crayons Indie Profilers Software Chasers The Blue Bird The Experienced dude Search Engine BanditsBox of Crayons Indie Profilers Software Chasers The Blue Bird The Experienced dude Search Engine BanditsSocial Geek Made Box of Crayons Moving Bird Made by Me Center for Creative Coding
2024 | Dec | 1097241 | The Experienced dude Static Startup 2 | Not Active | 808678 | Java Dalia The Successful Project Static Startup | IT | High | Completed | Suzan Mike | Esra Mejid | Mei Lee | Bernard Suppremilo | QA Tester 7 | 170 | 1863.3327 | 2023-06-25 | 2023-06-26 | 2023-10-28 | 2023-11-28 | 2024-01-30 | 2024-01-31 | Active Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingActive Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingThe Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob Geeklords
2025 | Oct | 1159144 | Debug Entity Robust Routine | Not Active | 1291996 | The Domain of Work Wombat Annual Award Show The Successful Project Software Chasers | Client | Normal | Completed | Ali Adam | Esra Mejid | Scot Bridgeton | Jamie Foxxie | QA Tester 3 | 63 | 1003.4668 | 2023-06-29 | 2023-06-30 | 2023-11-01 | 2023-12-02 | 2024-02-03 | 2024-02-04 | 7th Annual Workshop Wide Stringer Match of Health The Domain of Work Wombat7th Annual Workshop Wide Stringer Match of Health The Domain of Work WombatThe Successful Project Software Chasers 7th Annual Workshop Fast & Creative Gang Gob Geeklords
2023 | Jul | 1080464 | The Coding Expert Fast Coding | Active | 2006035 | Social Geek Made Box of Crayons The Successful Project Made by Me Center for Creative Coding | Fast Path | Normal | Resource Assignment | Ali Adam | Esra Mejid | Gerland Singh | Mary Frittle | QA Tester 3 | 192 | 535.0134 | 2023-07-04 | 2023-07-05 | 2023-11-06 | 2023-12-07 | 2024-02-08 | 2024-02-09 | The Blue Bird The Experienced dude The Domain of Work Social Geek Made Box of CrayonsThe Blue Bird The Experienced dude The Domain of Work Social Geek Made Box of CrayonsMade by Me Center for Creative Coding Fast & Creative Gang The Discovery of Era Enter Coding
2025 | Jan | 1078298 | Celestial Interface Gob Geeklords | Active | 147850 | Box of Crayons Indie Profilers Software Chasers Center for Creative Coding Search Engine Bandits | Security | Low | Research | Eddy Verly | Esra Mejid | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 348 | 175.5028 | 2023-07-07 | 2023-07-08 | 2023-11-09 | 2023-12-10 | 2024-02-11 | 2024-02-12 | Excel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineExcel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineThe Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob Geeklords
2024 | Dec | 1093153 | Excalibur GHI Training Impact Training | Active | 19165 | Made by Me Center for Creative Coding The Blue Bird The Discovery of Era Enter Coding | Security | Low | Approved for Deployment | Suzan Mike | Esra Mejid | Daniel Francis | Matthew Krillen | QA Tester 5 | 339 | 480.4958 | 2023-07-14 | 2023-07-15 | 2023-11-16 | 2023-12-17 | 2024-02-18 | 2024-02-19 | Social Geek Made Box of Crayons Moving Bird Made by Me Center for Creative CodingSocial Geek Made Box of Crayons Moving Bird Made by Me Center for Creative CodingThe Discovery of Era Enter Coding Social Geek Made Remembering Our Ancestors Fast Coding
2024 | Oct | 1176726 | Open Source Pundits Celestial Interface | Active | 363846 | The Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob Geeklords | Fast Path | Normal | Completed | Ali Adam | Eto Smith | Mei Lee | Bobby Guillman | QA Tester 2 | 323 | 1508.6421 | 2023-05-15 | 2023-05-16 | 2023-09-17 | 2023-10-18 | 2023-12-20 | 2023-12-21 | A Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityA Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityStatic Startup Fast & Creative Gang Indie Profilers
2025 | Jul | 1221262 | The Network The Social Experiment | Active | 91477 | Charged by Codes Java Dalia The Coding Master The Experienced dude Static Startup | Security | Normal | Completed | Ali Adam | Eto Smith | Gerland Singh | Bobby Guillman | QA Tester 1 | 268 | 857.258 | 2023-05-16 | 2023-05-17 | 2023-09-18 | 2023-10-19 | 2023-12-21 | 2023-12-22 | Coding Region The Principal of Change The Network Mentee to Mentor Mo-Money MasterclassCoding Region The Principal of Change The Network Mentee to Mentor Mo-Money MasterclassThe Experienced dude Static Startup The Art of Codes
2024 | Nov | 1113587 | The Experienced dude Static Startup 4 | Not Active | 377108 | The Experienced dude Static Startup Wombat Box of Crayons Indie Profilers | Security | Normal | Completed | Ali Adam | Eto Smith | Gerland Singh | Bobby Guillman | QA Tester 2 | 289 | 2105.5445 | 2023-05-20 | 2023-05-21 | 2023-09-22 | 2023-10-23 | 2023-12-25 | 2023-12-26 | A Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityA Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityThe Coding Master Celestial Interface Debug Entity The Art of Codes Open Source Pundits
2025 | Nov | 1236730 | The Experienced dude Static Startup 11 | Active | 460879 | The Network Linkage, Inc. Project Explained Town Hall Meeting Switch and Swift | Fast Path | Normal | Completed | Ali Adam | Eto Smith | Scot Bridgeton | Nate Matthers | QA Tester 9 | 356 | 814.3888 | 2023-06-21 | 2023-06-22 | 2023-10-24 | 2023-11-24 | 2024-01-26 | 2024-01-27 | The Social Experiment Coding League The Success The Network Linkage, Inc.The Social Experiment Coding League The Success The Network Linkage, Inc.Town Hall Meeting Switch and Swift The Social Experiment Coding Region The Principal of Change
2023 | Jul | 1131697 | The Experienced dude Static Startup 15 | Active | 713185 | The Success The GFI with Codes Remembering Our Ancestors Project Explained Code Change Group | Security | Normal | Development - Ops | Suzan Mike | Eto Smith | Whittney Huttson | Valerie Lazer | QA Tester 3 | 332 | 1881.3556 | 2023-07-16 | 2023-07-17 | 2023-11-18 | 2023-12-19 | 2024-02-20 | 2024-02-21 | Meetup for the Good The Coding Expert The Discovery of Era The Success The GFI with CodesMeetup for the Good The Coding Expert The Discovery of Era The Success The GFI with CodesProject Explained Code Change Group Meetup for the Good The Social Experiment Coding League
2025 | May | 1179160 | Excel and Elevate Training Active Achievement | Active | 2195918 | Fast & Creative Gang Gob Geeklords Robust Routine The Coding Master Celestial Interface | Security | Normal | Resource Assignment | Eddy Verly | Kate Mills | Daniel Francis | Bobby Guillman | QA Tester 2 | 314 | 186.7471 | 2023-05-11 | 2023-05-12 | 2023-09-13 | 2023-10-14 | 2023-12-16 | 2023-12-17 | The Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob GeeklordsThe Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob GeeklordsThe Coding Master Celestial Interface Debug Entity The Art of Codes Open Source Pundits
2023 | Sep | 1075642 | Enter Coding Center for Creative Coding | Active | 2062489 | Remembering Our Ancestors Fast Coding The Art of Codes Meetup for the Good The Coding Expert | IT | Normal | Development - Security | Jean Zac | Kate Mills | Whittney Huttson | Eddy Vertil | QA Tester 7 | 114 | 551.1658 | 2023-05-12 | 2023-05-13 | 2023-09-14 | 2023-10-15 | 2023-12-17 | 2023-12-18 | The Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast CodingThe Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast CodingMeetup for the Good The Coding Expert Charged by Codes The Success The GFI with Codes
2024 | Nov | 1097151 | The Experienced dude Static Startup 7 | Active | 1977991 | Excalibur Training Town Hall Meeting Robust Routine | IT | Normal | Completed | Suzan Mike | Kate Mills | Mei Lee | Eddy Vertil | QA Tester 2 | 94 | 2096.6973 | 2023-05-23 | 2023-05-24 | 2023-09-25 | 2023-10-26 | 2023-12-28 | 2023-12-29 | 7th Annual Workshop Wide Stringer Match of Health The Domain of Work Wombat7th Annual Workshop Wide Stringer Match of Health The Domain of Work WombatThe Social Experiment Coding League Center for Creative Coding The Network Linkage, Inc.
2025 | Oct | 1260505 | Fast Coding Enter Coding | Active | 1892566 | Remembering Our Ancestors Fast Coding Made by Me Meetup for the Good The Coding Expert | IT | Normal | Completed | Ali Adam | Kate Mills | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 112 | 2189.269 | 2023-05-24 | 2023-05-25 | 2023-09-26 | 2023-10-27 | 2023-12-29 | 2023-12-30 | The Discovery of Era Enter Coding Social Geek Made Remembering Our Ancestors Fast CodingThe Discovery of Era Enter Coding Social Geek Made Remembering Our Ancestors Fast CodingMeetup for the Good The Coding Expert The Discovery of Era The Success The GFI with Codes
2024 | Dec | 1101761 | The Domain of Work 7th Annual Workshop | Active | 2134273 | Match of Health Debug Entity Switch and Swift Annual Award Show White Feather | Client | Normal | Completed | Jean Zac | Mo Salah | Scot Bridgeton | Barbie Clainton | QA Tester 3 | 33 | 3.2776 | 2023-05-27 | 2023-05-28 | 2023-09-29 | 2023-10-30 | 2024-01-01 | 2024-01-02 | A Salute to New Workers Robust Routine Linkage, Inc. Match of Health Debug EntityA Salute to New Workers Robust Routine Linkage, Inc. Match of Health Debug EntityAnnual Award Show White Feather The Principal of Change 7th Annual Workshop Wide Stringer
2025 | Sep | 1253615 | Linkage, Inc. Coding League | Active | 1058186 | The Blue Bird The Experienced dude The Domain of Work Social Geek Made Box of Crayons | Client - Global | Normal | Requirements | Ali Adam | Kate Mills | Daniel Francis | Ellis Florzak | QA Tester 3 | 126 | 425.9006 | 2023-05-29 | 2023-05-30 | 2023-10-01 | 2023-11-01 | 2024-01-03 | 2024-01-04 | Moving Bird Charged by Codes 7th Annual Workshop The Blue Bird The Experienced dudeMoving Bird Charged by Codes 7th Annual Workshop The Blue Bird The Experienced dudeSocial Geek Made Box of Crayons The Successful Project Made by Me Center for Creative Coding
2025 | Apr | 1114381 | The Successful Project The Domain of Work | Active | 68259 | Match of Health Debug Entity Excel and Elevate Training Annual Award Show White Feather | Operations - Global | Normal | Resource Assignment | Jean Zac | Abd Elfattah Elsisi | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 252 | 95.718 | 2023-06-01 | 2023-06-02 | 2023-10-04 | 2023-11-04 | 2024-01-06 | 2024-01-07 | A Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityA Salute to New Workers Robust Routine Active Achievement Match of Health Debug EntityAnnual Award Show White Feather A Salute to New Workers 7th Annual Workshop Wide Stringer
2024 | Jul | 1097251 | Center for Creative Coding Box of Crayons | Active | 1474038 | Project Explained Code Change Group Meetup for the Good The Social Experiment Coding League | Client | Normal | Resource Assignment | Ali Adam | Kate Mills | Whittney Huttson | Ashley Queenie | QA Tester 5 | 40 | 286.3902 | 2023-06-04 | 2023-06-05 | 2023-10-07 | 2023-11-07 | 2024-01-09 | 2024-01-10 | The Success The GFI with Codes Remembering Our Ancestors Project Explained Code Change GroupThe Success The GFI with Codes Remembering Our Ancestors Project Explained Code Change GroupThe Social Experiment Coding League The Success The Network Linkage, Inc.
2023 | Aug | 1118371 | Box of Crayons The Experienced dude | Active | 1731089 | Project Explained Code Change Group Box of Crayons The Social Experiment Coding League | IT | Normal | Development - Ops | Suzan Mike | Farid Ahmed | Gerland Singh | Vergil Vimero | QA Tester 2 | 91 | 2011.2859 | 2023-06-09 | 2023-06-10 | 2023-10-12 | 2023-11-12 | 2024-01-14 | 2024-01-15 | The Success The GFI with Codes The Experienced dude Project Explained Code Change GroupThe Success The GFI with Codes The Experienced dude Project Explained Code Change GroupThe Social Experiment Coding League Center for Creative Coding The Network Linkage, Inc.
2023 | May | 1232538 | Social Geek Made The Blue Bird | Active | 705928 | A Salute to New Workers Robust Routine Linkage, Inc. Match of Health Debug Entity | IT | Normal | Task and Hours | Eddy Verly | Kate Mills | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 110 | 159.7183 | 2023-06-13 | 2023-06-14 | 2023-10-16 | 2023-11-16 | 2024-01-18 | 2024-01-19 | Excel and Elevate Training Excalibur Training Coding League A Salute to New Workers Robust RoutineExcel and Elevate Training Excalibur Training Coding League A Salute to New Workers Robust RoutineMatch of Health Debug Entity Switch and Swift Annual Award Show White Feather
2023 | Feb | 1297183 | Meetup for the Good Remembering Our | Active | 582134 | Annual Award Show White Feather The Principal of Change 7th Annual Workshop Wide Stringer | Client - Global | Normal | New | Ali Adam | Kate Mills | Whittney Huttson | Eddy Vertil | QA Tester 3 | 121 | 1899.128 | 2023-06-15 | 2023-06-16 | 2023-10-18 | 2023-11-18 | 2024-01-20 | 2024-01-21 | Match of Health Debug Entity Switch and Swift Annual Award Show White FeatherMatch of Health Debug Entity Switch and Swift Annual Award Show White Feather7th Annual Workshop Wide Stringer Mo-Money Masterclass The Domain of Work Wombat
2023 | May | 1215509 | Java Dalia Open Source Pundits | Active | 449074 | Static Startup Fast & Creative Gang Indie Profilers | IT | Normal | Resource Assignment - HOLD | Ali Adam | Hossam Khalil | Mei Lee | Bobby Silvermen | QA Tester 3 | 172 | 1644.6639 | 2023-06-20 | 2023-06-21 | 2023-10-23 | 2023-11-23 | 2024-01-25 | 2024-01-26 | Active Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingActive Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingFast & Creative Gang Gob Geeklords Robust Routine The Coding Master Celestial Interface
2024 | Feb | 988245 | Static Startup Java Dalia | Active | 202440 | Fast & Creative Gang Gob Geeklords Robust Routine The Coding Master Celestial Interface | Operations | Normal | Completed | Suzan Mike | Kate Mills | Scot Bridgeton | Amy Zimmerman | QA Tester 3 | 221 | 229.7327 | 2023-06-27 | 2023-06-28 | 2023-10-30 | 2023-11-30 | 2024-02-01 | 2024-02-02 | Excel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineExcel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineTown Hall Meeting Switch and Swift Fast Coding Coding Region The Principal of Change
2024 | Oct | 1159114 | The Experienced dude Static Startup 17 | Not Active | 1631076 | The Successful Project Software Chasers 7th Annual Workshop Fast & Creative Gang Gob Geeklords | Operations | Normal | Completed | Ali Adam | Kate Mills | Whittney Huttson | Kenneth Wright | QA Tester 5 | 225 | 1671.1464 | 2023-07-01 | 2023-07-02 | 2023-11-03 | 2023-12-04 | 2024-02-05 | 2024-02-06 | The Domain of Work Wombat Annual Award Show The Successful Project Software ChasersThe Domain of Work Wombat Annual Award Show The Successful Project Software ChasersFast & Creative Gang Gob Geeklords The Domain of Work The Coding Master Celestial Interface
2024 | Mar | 1162318 | The Principal of Change Switch and Swift | Active | 615544 | The Coding Master Celestial Interface Debug Entity The Art of Codes Open Source Pundits | Operations - Global | Normal | Completed | Suzan Mike | Kate Mills | Whittney Huttson | Seth Pence | QA Tester 3 | 255 | 64.3533 | 2023-07-03 | 2023-07-04 | 2023-11-05 | 2023-12-06 | 2024-02-07 | 2024-02-08 | Fast & Creative Gang Gob Geeklords Robust Routine The Coding Master Celestial InterfaceFast & Creative Gang Gob Geeklords Robust Routine The Coding Master Celestial InterfaceThe Art of Codes Open Source Pundits White Feather Charged by Codes Java Dalia
2023 | Nov | 1020142 | The Social Experiment Project Explained | Active | 622447 | Charged by Codes Java Dalia Wide Stringer The Experienced dude Static Startup | IT | Normal | Testing - Client | Suzan Mike | Sahar Rashad | Mei Lee | Arthur Knight | QA Tester 5 | 162 | 506.43 | 2023-07-05 | 2023-07-06 | 2023-11-07 | 2023-12-08 | 2024-02-09 | 2024-02-10 | The Art of Codes Open Source Pundits White Feather Charged by Codes Java DaliaThe Art of Codes Open Source Pundits White Feather Charged by Codes Java DaliaThe Experienced dude Static Startup Wombat Box of Crayons Indie Profilers
2024 | Aug | 1109819 | The Experienced dude Static Startup 10 | Active | 2087922 | The Network Linkage, Inc. Enter Coding Town Hall Meeting Switch and Swift | Fast Path | Normal | Resource Assignment | Ali Adam | Kate Mills | Daniel Francis | Brad Summers | QA Tester 3 | 72 | 1168.8911 | 2023-07-10 | 2023-07-11 | 2023-11-12 | 2023-12-13 | 2024-02-14 | 2024-02-15 | The Social Experiment Coding League Center for Creative Coding The Network Linkage, Inc.The Social Experiment Coding League Center for Creative Coding The Network Linkage, Inc.Town Hall Meeting Switch and Swift Fast Coding Coding Region The Principal of Change
2023 | Jun | 1148051 | The Experienced dude Static Startup 3 | Active | 781749 | The Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob Geeklords | IT | Normal | Resource Assignment | Suzan Mike | KMK | Daniel Francis | Security Project Management | QA Tester 3 | 129 | 1742.1342 | 2023-07-12 | 2023-07-13 | 2023-11-14 | 2023-12-15 | 2024-02-16 | 2024-02-17 | Excel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineExcel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust RoutineThe Experienced dude Static Startup Wombat Box of Crayons Indie Profilers
2024 | Mar | 1097150 | Mo-Money Masterclass The Principal of Change | Active | 1605831 | The Coding Master Celestial Interface The Successful Project The Art of Codes Open Source Pundits | Operations | Normal | New | Ali Adam | Kate Mills | Whittney Huttson | Project Management | QA Tester 3 | 40 | 1928.6767 | 2023-07-13 | 2023-07-14 | 2023-11-15 | 2023-12-16 | 2024-02-17 | 2024-02-18 | The Network Linkage, Inc. Project Explained Town Hall Meeting Switch and SwiftThe Network Linkage, Inc. Project Explained Town Hall Meeting Switch and SwiftThe Art of Codes Open Source Pundits Fast & Creative Gang Charged by Codes Java Dalia
2024 | Jul | 1097202 | Excalibur Training Impact Training | Active | 1276392 | The Discovery of Era Enter Coding Social Geek Made Remembering Our Ancestors Fast Coding | Client - Global | Normal | Completed | Suzan Mike | Sam Jack | Whittney Huttson | Keri Waves | QA Tester 3 | 63 | 323.5026 | 2023-05-09 | 2023-05-10 | 2023-09-11 | 2023-10-12 | 2023-12-14 | 2023-12-15 | Made by Me Center for Creative Coding The Blue Bird The Discovery of Era Enter CodingMade by Me Center for Creative Coding The Blue Bird The Discovery of Era Enter CodingRemembering Our Ancestors Fast Coding Made by Me Meetup for the Good The Coding Expert
2025 | Jan | 1020663 | Active Achievement Mentee to Mentor | Not Active | 938369 | Excel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust Routine | Client - Global | High | Completed | Suzan Mike | KMK | Daniel Francis | Eddy Vertil | QA Tester 3 | 56 | 1953.6276 | 2023-05-26 | 2023-05-27 | 2023-09-28 | 2023-10-29 | 2023-12-31 | 2024-01-01 | Active Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingActive Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingA Salute to New Workers Robust Routine Active Achievement Match of Health Debug Entity
2024 | May | 1101806 | Gob Geeklords Software Chasers | Not Active | 1469801 | The Principal of Change Project Explained Mo-Money Masterclass | Client | Normal | Cancelled | Suzan Mike | Sam Jack | Mei Lee | Eddy Vertil | QA Tester 2 | 18 | 94.9551 | 2023-05-28 | 2023-05-29 | 2023-09-30 | 2023-10-31 | 2024-01-02 | 2024-01-03 | Active Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingActive Achievement Impact Training Coding Region Excel and Elevate Training Excalibur TrainingBox of Crayons Indie Profilers Software Chasers Center for Creative Coding Search Engine Bandits
2023 | Oct | 1077403 | pp | Active | 4354263 | Made by Me Center for Creative Coding Fast & Creative Gang The Discovery of Era Enter Coding | IT | Normal | Testing - IT | Eddy Verly | Sam Jack | Mei Lee | Eddy Vertil | QA Tester 7 | 148 | 1502.9552 | 2023-05-30 | 2023-05-31 | 2023-10-02 | 2023-11-02 | 2024-01-04 | 2024-01-05 | Social Geek Made Box of Crayons The Successful Project Made by Me Center for Creative CodingSocial Geek Made Box of Crayons The Successful Project Made by Me Center for Creative CodingThe Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast Coding
2025 | May | 1157668 | The Experienced dude Static Startup 19 | Not Active | 387692 | Town Hall Meeting Switch and Swift The Social Experiment Coding Region The Principal of Change | Operations - Global | High | Completed | Ali Adam | Rovan Hossam | Daniel Francis | Project Management | QA Tester 3 | 229 | 2170.4729 | 2023-06-03 | 2023-06-04 | 2023-10-06 | 2023-11-06 | 2024-01-08 | 2024-01-09 | The Network Linkage, Inc. Project Explained Town Hall Meeting Switch and SwiftThe Network Linkage, Inc. Project Explained Town Hall Meeting Switch and SwiftCoding Region The Principal of Change The Network Mentee to Mentor Mo-Money Masterclass
2025 | Feb | 1081039 | The Coding Master Fast & Creative Gang | Not Active | 1097570 | Meetup for the Good The Coding Expert The Discovery of Era The Success The GFI with Codes | Client - Global | Normal | Completed | Ali Adam | Haidy Hussain | Daniel Francis | Barbie Clainton | QA Tester 8 | 55 | 2048.8717 | 2023-06-06 | 2023-06-07 | 2023-10-09 | 2023-11-09 | 2024-01-11 | 2024-01-12 | Remembering Our Ancestors Fast Coding Made by Me Meetup for the Good The Coding ExpertRemembering Our Ancestors Fast Coding Made by Me Meetup for the Good The Coding ExpertThe Success The GFI with Codes Remembering Our Ancestors Project Explained Code Change Group
2024 | Aug | 1082757 | Software Chasers Wombat | Active | 2066209 | The Success The GFI with Codes The Experienced dude Project Explained Code Change Group | Operations | Normal | Completed | Eddy Verly | Sam Jack | Mei Lee | Eddy Vertil | QA Tester 3 | 198 | 1195.5234 | 2023-06-10 | 2023-06-11 | 2023-10-13 | 2023-11-13 | 2024-01-15 | 2024-01-16 | The Coding Master Celestial Interface The Successful Project The Art of Codes Open Source PunditsThe Coding Master Celestial Interface The Successful Project The Art of Codes Open Source PunditsThe Principal of Change Project Explained Mo-Money Masterclass
2023 | Sep | 1092547 | Project Explained The Success | Active | 1344257 | Box of Crayons Indie Profilers Software Chasers The Blue Bird The Experienced dude Search Engine Bandits | Client - Global | Normal | Testing - IT | Suzan Mike | Ahmed Khalil | Gerland Singh | Vergil Vimero | QA Tester 2 | 84 | 1420.7068 | 2023-06-11 | 2023-06-12 | 2023-10-14 | 2023-11-14 | 2024-01-16 | 2024-01-17 | The Experienced dude Static Startup Wombat Box of Crayons Indie ProfilersThe Experienced dude Static Startup Wombat Box of Crayons Indie ProfilersThe Blue Bird The Experienced dude Search Engine Bandits In Recognition of Codes Social Geek Made Box of Crayons
2024 | Jun | 1112502 | Coding Region Town Hall Meeting | Active | 1828852 | Coding Region The Principal of Change The Network Mentee to Mentor Mo-Money Masterclass | Fast Path | Normal | Task and Hours | Eddy Verly | Sam Jack | Mei Lee | Eddy Vertil | QA Tester 3 | 55 | 1339.6972 | 2023-06-18 | 2023-06-19 | 2023-10-21 | 2023-11-21 | 2024-01-23 | 2024-01-24 | Town Hall Meeting Switch and Swift The Social Experiment Coding Region The Principal of ChangeTown Hall Meeting Switch and Swift The Social Experiment Coding Region The Principal of ChangeMentee to Mentor Mo-Money Masterclass Town Hall Meeting Active Achievement Impact Training
2025 | Jun | 1163655 | The Success Meetup for the Good | Not Active | 50683 | Annual Award Show White Feather A Salute to New Workers 7th Annual Workshop Wide Stringer | IT | Normal | Cancelled | Ali Adam | Sam Jack | Gerland Singh | Wayne Bruceton | QA Tester 2 | 55 | 1424.5446 | 2023-06-19 | 2023-06-20 | 2023-10-22 | 2023-11-22 | 2024-01-24 | 2024-01-25 | Match of Health Debug Entity Excel and Elevate Training Annual Award Show White FeatherMatch of Health Debug Entity Excel and Elevate Training Annual Award Show White Feather7th Annual Workshop Wide Stringer Match of Health The Domain of Work Wombat
2024 | Feb | 1141994 | The Experienced dude Charged by Codes | Active | 2100300 | Moving Bird Charged by Codes 7th Annual Workshop The Blue Bird The Experienced dude | IT | High | Scheduled for Deployment | Eddy Verly | Sam Jack | Mei Lee | Nicolas Centrio | QA Tester 3 | 157 | 1144.4193 | 2023-06-26 | 2023-06-27 | 2023-10-29 | 2023-11-29 | 2024-01-31 | 2024-02-01 | In Recognition of Codes The Art of Codes Annual Award Show Moving Bird Charged by CodesIn Recognition of Codes The Art of Codes Annual Award Show Moving Bird Charged by CodesThe Blue Bird The Experienced dude The Domain of Work Social Geek Made Box of Crayons
2023 | Apr | 1295673 | The Discovery of Era Made by Me | Active | 1175427 | Active Achievement Impact Training Code Change Group Excel and Elevate Training Excalibur Training | IT | Normal | Requirements | Ali Adam | Sam Jack | Scot Bridgeton | Eddy Vertil | QA Tester 3 | 78 | 934.7705 | 2023-06-28 | 2023-06-29 | 2023-10-31 | 2023-12-01 | 2024-02-02 | 2024-02-03 | Mentee to Mentor Mo-Money Masterclass The GFI with Codes Active Achievement Impact TrainingMentee to Mentor Mo-Money Masterclass The GFI with Codes Active Achievement Impact TrainingExcel and Elevate Training Excalibur Training Coding League A Salute to New Workers Robust Routine
2023 | Nov | 1142784 | Remembering Our Ancestors The Discovery | Active | 1939802 | Active Achievement Impact Training Coding Region Excel and Elevate Training Excalibur Training | Client - Global | Normal | Testing - Ops | Ali Adam | Sam Jack | Whittney Huttson | Christine Dayton | QA Tester 4 | 40 | 257.9659 | 2023-07-02 | 2023-07-03 | 2023-11-04 | 2023-12-05 | 2024-02-06 | 2024-02-07 | Mentee to Mentor Mo-Money Masterclass Town Hall Meeting Active Achievement Impact TrainingMentee to Mentor Mo-Money Masterclass Town Hall Meeting Active Achievement Impact TrainingExcel and Elevate Training Excalibur Training Mentee to Mentor A Salute to New Workers Robust Routine
2025 | Jun | 1159126 | Robust Routine Excalibur Training | Not Active | 100345 | The Domain of Work Wombat Impact Training The Successful Project Software Chasers | Client - Global | High | Completed | Jean Zac | Sam Jack | Scot Bridgeton | Nicolas Centrio | QA Tester 8 | 187 | 407.2477 | 2023-07-06 | 2023-07-07 | 2023-11-08 | 2023-12-09 | 2024-02-10 | 2024-02-11 | 7th Annual Workshop Wide Stringer Mo-Money Masterclass The Domain of Work Wombat7th Annual Workshop Wide Stringer Mo-Money Masterclass The Domain of Work WombatThe Successful Project Software Chasers Excalibur Training Fast & Creative Gang Gob Geeklords
2024 | May | 1156107 | Code Change Group The GFI with Codes | Active | 787311 | The Art of Codes Open Source Pundits White Feather Charged by Codes Java Dalia | IT | Low | Requirements | Jean Zac | Sam Jack | Gerland Singh | Shakena Underwood | QA Tester 5 | 74 | 683.3497 | 2023-07-08 | 2023-07-09 | 2023-11-10 | 2023-12-11 | 2024-02-12 | 2024-02-13 | The Coding Master Celestial Interface Debug Entity The Art of Codes Open Source PunditsThe Coding Master Celestial Interface Debug Entity The Art of Codes Open Source PunditsCharged by Codes Java Dalia Wide Stringer The Experienced dude Static Startup
2023 | Jan | 1266200 | Mentee to Mentor Coding Region | Not Active | 1069260 | Excel and Elevate Training Excalibur Training Coding League A Salute to New Workers Robust Routine | Client - Global | Normal | Cancelled | Ali Adam | Sam Jack | Scot Bridgeton | Karen Rittleton | QA Tester 5 | 81 | 81.0775 | 2023-07-11 | 2023-07-12 | 2023-11-13 | 2023-12-14 | 2024-02-15 | 2024-02-16 | Active Achievement Impact Training Code Change Group Excel and Elevate Training Excalibur TrainingActive Achievement Impact Training Code Change Group Excel and Elevate Training Excalibur TrainingA Salute to New Workers Robust Routine Linkage, Inc. Match of Health Debug Entity
Note on P1: Full-time equivalent

## KPIS & TABLES
Sum of Project Value | Count of Project ID Number | Sum of FTE Savings | Sum of Working Hours | Distinct Count of Developers | Row Labels | Count of Project ID Number | Row Labels | Count of Project ID Number | Row Labels | Count of Project ID Number | Row Labels | Count of Project ID Number | Row Labels | Count of Project ID Number | [5 empty] | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels | Row Labels
2750430 | 2 | 103 | 609.8927 | 2 | Client | 1 | Normal | 2 | Active | 2 | Completed | 1 | Client | 1 |  |  |  |  | 2023-05-12 | 13-05-2023 | 2023-09-14 | 1075642 | IT | Normal | QA Tester 7 | 2023-10-15 | 2023-12-17 | 2023-12-18 | Whittney Huttson | Eddy Vertil | The Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast CodingThe Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast CodingMeetup for the Good The Coding Expert Charged by Codes The Success The GFI with Codes
[5 empty] | Client - Global | 1 | Grand Total | 2 | Grand Total | 2 | Resource Assignment | 1 | Client - Global | 1 | - | - | 1 | - | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | Grand Total
[5 empty] | Fast Path | 1 |  |  |  |  | Grand Total | 2 | Grand Total | 2 | - | - | 2
[5 empty] | Operations | 1
[5 empty] | Security | 2 | [10 empty] | -
[5 empty] | Grand Total | 6 | [10 empty] | -
-
-
-
-
1
-
-
-
-
-
-
1
KPI LINK TOWARDS PIVOT TABLE
Click Here
To
Access Dashboard
Click Here
To
Access Dashboard

## dashboard
YEAR
MONTH
Project Value
Total Project
2
projects
103
FTE Savings
Working Hours
USD
610
Total Devloper
2
devs.
1
Completed
On Hold
1
-
On Going
Cancelled
-
Project
Priority
-
HIGH
NORMAL
2
LOW
-
Projects Status
Project Milestone
Project Completed
1
-
-
-
-
-
-
-
1
-
-
-
-
-
shedule for devlopment
Aproved for deployment
Testing client
Testing
IT
Testing
Ops
Requirment
Devlopment
Ops
devlopment
security
Task and Hours
Resourse
Assignment
Resourse
Assignment-2
Research
New
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
$27,50,430
Hrs.
Active
Not Active
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Start Date
12 May 2023
Dev Start Date
Internal Testing Date
Project ID
Project Type
ITQA
Target client Testing Date
Actual Deployment Date
Target Deployment Date
Business Analyst
Next Action
13-05-2023
14 September 2023
1075642
IT
QA Tester 7
15 October 2023
17 December 2023
18 December 2023
Whittney Huttson
Eddy Vertil
Manager comments
The Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast CodingThe Discovery of Era Enter Coding The Coding Master Remembering Our Ancestors Fast CodingMeetup for the Good The Coding Expert Charged by Codes The Success The GFI wi
Projects Types